## Slide 1: NYL / iPipeline Annuity Release Plan PHASE 1.0 4/2/2015

## Slide 2: NYL iGO eApp – Phase 1
 | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3
 | 4/6/15 to 4/10/15 | 4/13/15 to 4/24/15 | 4/27/15 to 5/8/15 | 5/11/15 to 5/22/15
 | Setup Setup Annuity channel Setup Dev environments Create NYL Annuity Products Requirements (Obtain Sign Off) Finalize open requirements L&J Owner Joint Owner Annuitant Joint Annuitant Applicant Integrations Establish Security Piece (SAML) MISC Align team on process | eApp Requirements SSO Spec Updated Payee Primary Beneficiaries Primary Beneficiaries (UGMA/UTMA) Cont Beneficiaries Cont Beneficiaries (UGMA/UTMA) Screens Case Info – modify Name label L&J Owner Joint Owner Annuitant Joint Annuitant Integrations Start PPfA Misc New Relic working with new channel | eApp Requirements Policy type Screen (4 grids) 1035 Exchange Rollovers Transfer Screens Applicant Payee Primary Beneficiaries Primary Beneficiaries (UGMA/UTMA) Cont Beneficiaries Cont Beneficiaries (UGMA/UTMA) Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Continue PPfA E-SUBMISSION – Previous sprints fields (create temp submision button which emails 103) Defect Support | eApp Requirements 1035 Exchange (State Specifics) 5304 Simple AR Replacement Foreign Owner - w8 form Screens Policy type Screen (4 grids) 1035 Exchange Rollovers Transfer Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Start SSO Continue PPfA E-SUBMISSION – Previous sprints fields Defect Support
 | Needed from NYL Sign off on Initiation Deliverables Sign SOW | Needed from NYL Document and Sign off on Sprint Requirements listed above Work on eSign Requirements/Spec | Needed from NYL Document and Sign off on Sprint Requirements listed above Work on eSign Requirements/Spec Provide SAML metadata for new channel User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above Work on eSign Requirements/Spec User Experience Performance Testing

## Slide 3: NYL iGO eApp – Phase 1
 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7
 | 5/25/15 to 6/5/15 | 6/8/15 to 6/19/15 | 6/22/15 to 7/3/15 | 7/6/15 to 7/17/15
 | eApp Requirements CA Replacements (same as Life) External Conversion Screen FL Replacements (Comparative Analysis Forms) Internal Conversion Screen RI Replacements (same as Life) Inherited IRA Screens 1035 Exchange (State Specifics) 5304 Simple AR Replacement Foreign Owner - w8 form Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Complete SSO Continue PPfA E-SUBMISSION – Previous sprints fields Defect Support | eApp Requirements NV Replacements WA Replacements (same as Life) WY Replacements Premium Riders Agent Statement screen Screens CA Replacements (same as Life) External Conversion Screen FL Replacements (Comparative Analysis Forms) Internal Conversion Screen RI Replacements (same as Life) Inherited IRA Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Continue PPfA E-SUBMISSION – Previous sprints fields Defect Support | eApp Requirements Check-o-matic (EFT) screen (move with Premium) Employer Billing Screen (move with Premium) Large Case Screen Investor Profile - Exchange/Replacement Screens NV Replacements WA Replacements (same as Life) WY Replacements Premium Riders Agent Statement screen Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Continue PPfA E-SUBMISSION – Previous sprints fields 9.0 Start screen conversions Defect Support | eApp Requirements Attachments Investor Profile - Intended Use/Product Info Investor Profile - Joint Owner Profile (remove) Investor Profile - Owner Profile (remove) Investor Profile - Source of Funds Screens Check-o-matic (EFT) screen Employer Billing Screen Large Case Screen Investor Profile - Exchange/Replacement Start Shared eSignature Screens Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Continue PPfA E-SUBMISSION – Previous sprints fields Replacement List Integration 9.0 Cont screen conversions Defect Support
 | Needed from NYL Document and Sign off on Sprint Requirements listed above Work on eSign Requirements/Spec User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above Work on eSign Requirements/Spec User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above Sign off on eSignature Spec Deliver WSDL and active endpoint for Replacement List Integration User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing

## Slide 4: NYL iGO eApp – Phase 1
 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11
 | 7/20/15 to 7/31/15 | 8/3/15 to 8/14/15 | 8/17/15 to 8/28/15 | 8/31/15 to 9/11/15
iPipeline | eApp Requirements Investor Profile - Source of Funds - Income Benefit Rider Investor Profile - Source of Funds - Investment Division Allocations Screens Cont Shared eSignature Screens Attachments Investor Profile - Intended Use/Product Info Investor Profile - Joint Owner Profile (remove) Investor Profile - Owner Profile (remove) Investor Profile - Source of Funds Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Continue PPfA E-SUBMISSION – Previous sprints fields ADDRESS VALIDATION 9.0 Cont screen conversions Defect Support | eApp Requirements Investor Profile - Source of Funds - Investment Objective Investor Profile - Source of Funds - Risk Tolerance/ Investment Objectives (Variable) Investor Profile - Source of Funds - Risk Tolerance / Investment Objectives (Income Plus) Investor Profile - Source of Funds - Suitability Disclosure Reg 60 Screen Screens Complete Shared eSignature Screens Investor Profile - Source of Funds - Income Benefit Rider Start Investor Profile - Source of Funds - Investment Division Allocations Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations Complete PPfA E-SUBMISSION – Previous sprints fields PORTAL ALERTS - Modify ID passed 9.0 Cont screen conversions Defect Support | eApp Requirements Investor Profile - Source of Funds - Time Horizon Investor Profile - Source of Funds - Total Score Summary Investor Profile - Source of Funds - Type of Investor Investor Profile - Source of Funds -GFIB Rider (remove) Screens Start Face 2 Face eSignature Screens Complete Investor Profile - Source of Funds - Investment Division Allocations Investor Profile - Source of Funds - Investment Objective Reg 60 Screen Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations E-SUBMISSION – Previous sprints fields 9.0 Cont screen conversions Defect Support | eApp Requirements NY Suitability screen Investor Profile - Source of Funds -Investment Options Audit Log Changes Screens Complete Face 2 Face eSignature Screens Investor Profile - Source of Funds - Risk Tolerance Investor Profile - Source of Funds - Risk Tolerance / Investment Objectives Investor Profile - Source of Funds - Suitability Disclosure Investor Profile - Source of Funds - Time Horizon Investor Profile - Source of Funds - Total Score Summary Investor Profile - Source of Funds - Type of Investor Investor Profile - Source of Funds -GFIB Rider (remove) Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations E-SUBMISSION – Previous sprints fields Reg 60 Integration 9.0 Complete screen conversions? Defect Support
 | Needed from NYL Document and Sign off on Sprint Requirements listed above Deliver WSDL and active endpoint for PORTAL ALERTS - Modify ID passed User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above Deliver WSDL and active endpoint for Reg 60 Integration User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing

## Slide 5: NYL iGO eApp – Phase 1
 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15
 | 9/14/15 to 9/25/15 | 9/28/15 to 10/9/15 | 10/12/15 to 10/23/15 | 10/26/15 to 11/6/15
iPipeline | eApp Requirements eSignature Expiration - Apply entity expiry rules to Joint Owners (life only allows Owner as entity) Duplicate Screens Start Remote eSignature Screens NY Suitability screen Start Investor Profile - Source of Funds -Investment Options Forms/Mapping Map/Trigger forms to support previous sprint screens Start State Specific Forms triggers/mapping Integrations E-SUBMISSION – Previous sprints fields Defect Support | eApp Screens Complete Remote eSignature Screens Complete Investor Profile - Source of Funds -Investment Options Start Audit Log Changes Forms/Mapping Map/Trigger forms to support previous sprint screens Complete State Specific Forms triggers/mapping Integrations E-SUBMISSION – Previous sprints fields Defect Support | eApp Screens eSignature - Parent / Guardian Support Complete Audit Log Changes eSignature Expiration - Apply entity expiry rules to Joint Owners (life only allows Onwer as entity) Forms/Mapping Map/Trigger forms to support previous sprint screens Integrations E-SUBMISSION – Previous sprints fields Defect Support | eApp Screens Duplicate Forms/Mapping Map/Trigger forms to support previous sprint screens (ICC) Integrations E-SUBMISSION – Previous sprints fields Defect Support
 | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing | Needed from NYL Document and Sign off on Sprint Requirements listed above User Experience Performance Testing

## Slide 6: NYL iGO eApp – Phase 1
 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 16
 | 11/9/15 to 11/20/15 | 11/23/15 to 12/4/15 | 12/7/15 to 12/18/15 | 
iPipeline | Final UAT Support | Final UAT Support | Final UAT Support Pilot Production Rollout 12/18/15 | 
 | Final automated and load performance testing | Final automated and loadperformance testing |  | 

## Slide 7: Open Items
Item | Owner | Status | Details
Need Reporting Requirements | NYL | Open | Need to know changes to existing reports
Identify data changes to existing integrations | NYL | Open | 
When implement new Reg 60 design? | NYL | Open | Decision wont be available for another 2-3 weeks.
Schedule Dev onsite kickoff meeting | NYL/iPipe | Open | 
What are we using for defect tracking | NYL/iPipe | Open | 
Setup meeting with iPipe QA Director to discuss if we can modify our JIRA. | iPipe | Open | 
Replacement requirements |  |  | 
Add details to plan to identify where we are plugging in existing integrations |  |  | 
Add date to NYL integration deliverables |  |  | 
Add details on when we will be calling PPfA service |  |  | 
Add details when new servers will be available. |  |  | 
Setup Catchpoint scripts – what sprint? |  |  | 
Overflow – when will we know how may pages are needed? Once known NYL needs to update the forms with the pages. |  |  | 

## Slide 8: Open Items
Item | Owner | Status | Details
Move state specific replacement screens out and move investor profile up |  |  | 
Look at nyl 3.0 / 3.1 sprint schedule. |  |  | 
Is 9.0 still in scope for 2015? Uttara says hell no. |  |  | 
NYL confirming that they need the NB 21 number in the Portal Alert. |  |  | 
Remove Reg 60 Integration |  |  | 
Are we receiving the bank address in the bank validation? |  |  | 
Add the eDelivery story to ppt |  |  | 
Missing Replacement Screens: 5305 SEP, Cert of Deposit, and Mutual Funds |  |  | 
Do we need the Large Case screen? NYL to check | NYL |  | 
Build out min viable screens to submit case. Move up Investor Profile Move up eSignature | Hirl |  | 
Add browser testing to plan |  |  | 
Must revisit the Performance test plan to support Annuity. Do we need to add more users to the test. |  |  | 

## Slide 9
Revision History | Who/Role | 
4/1 | Hirl | Initial Revision
4/2 | Hirl | Added takeaways from onsite meeting