## Slide 1: Securian NGSD Project Release Plan-Revised 11/3/20
Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3
8/13 – 8/26 | 8/27 – 9/9 | 9/10 – 9/23 | 9/24 – 10/7
 | BA Pre-Project tasks (updates to workflow, BRD, content, etc.) DEV Pre-Project set up | NY Reg 60 NY Authorization NY Reg 187 NY Sales Material Proposed Insured Proposed Insured Continued Owner Identification Officer Identification Trustee Owner Corporation Grid (Owner Grid details; Trustee, Officer, Partner) Beneficiary Defect Resolution | Continue all of Sprint 1 Work NY Reg 60 NY Authorization NY Reg 187 NY Sales Material (Dev) Proposed Insured Proposed Insured Continued Owner Identification Officer Identification Trustee Owner Corporation Grid (Owner Grid details; Trustee, Officer, Partner) Beneficiary (Dev) No Mapping Included Defect Resolution | Underwriting Information Foreign Residence and Travel Military & Aviation Policy Date Existing Coverage and Replacement (Dev) Beneficiary (QA) Client Collaboration application setup (Dev) NY Sales Material QA Sprint 2 Mapping (partial) Defect Resolution
Securian | Prepare for testing No delivery to UAT | Prepare for testing iPipeline closed for the holiday on 9/7 | Prepare for testing | Sprint 2 Testing

## Slide 2: Securian NGSD Project Release Plan-Revised 11/3/20
Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7
10/8 – 10/21 | 10/22– 11/4 | 11/5 – 11/18 | 11/19 – 12/2
 | Premium & Billing Information Client Collaboration PI Write Fit Underwriting Pre-Qualification Write Fit Express Pre-Qualification (Dev) ADB for Chronic Illness Existing Coverage and Replacement (QA) Client Collaboration application setup (QA) Financial Supp-Personal (Dev) Sprint 2 Mapping (Dev) Defect Resolution | Write Fit Express UW Pre-Qualification (QA) Financial Supp-Personal (QA) Benefit Distribution Agreement Financial Supp-Business Purpose of Insurance Insurable Interest and Premium Financing Premium & Billing Information Cont. Representative Report/Agent Report (Dev) Representative Info/Agent Info (Dev) Solicitation Info (Dev) Representative Comments Application Attachments UW Options Tele Interview WriteFit UW Sprint 2 Mapping (QA) Sprint 3 Mapping Defect Resolution | Representative Report/Agent Report (QA) Representative Info/Agent Info (QA) Solicitation Info (QA) Sprint 3 Mapping(QA) Client Account Information Client Account Information Cont’d VUL Client Account Info-Broker/Dealer Affiliations Business Information Replacement Info (Washington, Wyoming) Replacement Memorandum-AR NY Preliminary Information Sports and Avocation Sports and Avocation Cont'd Life Insurance In Force and Replacement – NY EParamed NY Resident Solicitation Defect Resolution | Attending physician information Physician Information Policy Cost Income Protection EFT Enrollment Financial Services and Product Summary Disclosure Employee Benefit Plan Premium Deposit Interview Comments Sprint 4 & 5 Mapping Defect Resolution
Securian | Sprint 3 Testing | Sprint 4 Testing 5368, 5329, 5328 | Sprint 5 Testing 5364, 5330, 5386 | Sprint 6 Testing 5561, 5562, 5580, 5581, 5696, 5697 iPipeline closed for holidays 11/26-11/27

## Slide 3: Securian NGSD Project Release Plan-Revised 11/3/20
Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11
12/3 – 12/16 | 12/17– 12/30 | 12/31 – 1/13/2021 | 1/13 - 1/27/2021
 | 103 XML/ 121 (Dev) ALLFINANZ Sprint 5 & 6 Mapping | 103 XML/ 121 (QA) Alpha Trust (Dev) | Alpha Trust (Dev) Client Collaboration (Dev) Welcome Screen (PI Screen Updates) Allocation Options Allocation Options Cont. IUL Illustration Cert Sprint 6 & 7 Mapping Defect Resolution | Alpha Trust (QA) IUL Allocation Options SecureCare UL-Proposed Insured SecureCare UL-Life Insurance inForce and Replacement SecureCare UL-LTC Worksheet Client Collaboration (QA) Defect Resolution
Securian | Sprint 7 Testing | Sprint 8 Testing iPipeline closed for the Holiday on 12/25 and 1/1 | Sprint 9 Testing | Sprint 10 Testing

## Slide 4: Securian NGSD Project Release Plan-Revised 11/3/20
Sprint 12 | Sprint 13 | Sprint 14 | 
1/28 - 2/10 | 2/11 - 2/24 | 2/25 - 3/10 | 
 | Additional Mapping | Defect Resolution | Production Prep Defect Resolution | 
Securian | Sprint 11 Testing | Sprint 10 Testing Regression | Regression UAT Sign off TBD Prod Go Live TBD Note: TBD dates are due to merge from classic work (from Dedicated Team) to NGSD |